Biomarkers and Breast Cancer Risk Prediction in Young Women Working Group

Update to the Cohort Consortium Steering Committee

Presented by Anne Zeleniuch-Jacquotte

September 18, 2015

- How and when the working group or project was established

  - Grant proposal idea: Can we improve breast cancer risk prediction modeling in younger women using biomarkers?

  - Approached PIs of cohorts who recruited younger women (<50) and collected serum/plasma

  - Submitted a proposal to the Cohort Consortium which was approved in 2012

  - Submitted R01 in October 2012

  - Grant proposal was funded for 3 years (09/2013-08/2016)

- Number of cohorts participating

  - Initially 9 cohorts

  - Sister Study offered to contribute its data in 2014; so currently 10 cohorts

- Accomplishments so far

  - Grant is entering its third and last year; all assays have been completed; data harmonization ongoing

  - At least 4 publications planned

    - AMH and risk of breast cancer

    - AMH as predictor of age at menopause

    - Correlates of AMH

    - Risk prediction model

    - Possibly methodological papers on evaluation of risk prediction models

- Other projects that are building on this project / working group

  - Genetics of AMH (proposed by Tony Swerdlow)

- Success or challenges with the project

  - Challenges

    - Funded was delayed

      - Cohorts included mostly Caucasians so the Inclusion of minorities plan was deemed not appropriate

      - One of the co-investigators is NIH intramural, so the Program Director wanted to convert the grant into a U award

    - Lab doing AMH assays was closed – Had to find another lab and conduct pilot studies to assess assay performance (resulted in delay + additional costs)

    - Data collection and data harmonization

      - We started with data specification requests from the Vit D project (rare cancers and the breast and CRC projects), which helped ‘getting it right the first time’ and thus minimize burden on cohorts

      - However, data harmonization remains a major time-consuming task (definition of variables vary according to cohorts and defining common variables depends on the participating cohorts)

  - Successes

    - Very pleased with the collaboration. Cohorts have been extremely responsive.

    - Reasons:

      - History of collaboration

      - We have tried to minimized the burden for participating cohorts

      - For US cohorts, there is funding: Each of the US cohorts has a subcontract

- Ways the Steering Committee can be of help

  - Annual meeting is very helpful. Problem: Scheduling: this year most of the WG meetings are on Wed, so it will be possible to attend only a few of the WG meetings our cohort is part of. Scheduling more meetings on Friday would help reduce the overlap.

  - Data harmonization: Develop guidelines regarding ways to minimize repeating work that other consortia have done (Note: I would be happy to participate in such an effort).

7.      Lessons learned: what’s working, what’s not working, what could be improved or done differently

8.      What you would recommend to other working groups based on your experience in the Cohort Consortium

- Include appropriate funding for participating cohorts:  It helps to obtain data/samples in a timely fashion and to engage investigators